# RESOURCE ALLOCATION MAP

`

## WHY THIS TOOL MATTERS?

Projects often fail not because the idea is weak, but because the team discovers too late that time, materials, money or people were missing. A Resource Allocation Map helps you understand what you have, what you need, and how to distribute resources across each activity of your project.

For young teams, this tool:

- Prevents stress and last-minute problems

- Supports realistic planning

- Clarifies responsibilities

- Ensures that each activity has the people, materials, and budget it needs.

It is especially relevant in cultural mediation, where activities involve diverse tasks (creative work, communication, logistics, facilitation).

## HOW TO USE IT?

## 1/ List your project activities: Take your plan and write down each workshop, meeting, event, creation task, or communication action.

## 2/ Identify available resources: Think about human resources (team), materials and equipment, technical tools, spaces, and budget.

## 3/ Map resources to activities: For each activity, specify what is required and who/what already exists.

## 4/ Spot gaps: Identify what is missing: materials to borrow, volunteers to recruit, skills to develop, budget needed.

## 5/ Adjust the plan: Reallocate resources, reduce workload, or modify activities so everything becomes achievable.

## 6/ Update throughout the project: As things evolve, revisit and adjust the map.

## TIPS

  Be honest: overestimating your capacity leads to frustration.

  Start with what is free or already available (space, volunteers, materials).

  Ask partners in advance: many resources can be borrowed (rooms, equipment, expertise).

  Use colours (green = available, yellow = partially available, red = missing) for easy visualisation.

  Keep the map simple: students, youth workers, and volunteers must be able to read it instantly.

# TEMPLATE
Resource Allocation Map

## 1 - LIST OF PROJECT ACTIVITIES
What will you do?

| Activity description | Date / Duration | Responsible. |
| --- | --- | --- |

## 2 - WHAT RESOURCES DO WE HAVE?
Human, material, technical, financial, spaces

| Resource Type (Human, material, tecnical, space, budget…) | Source (team, partner, donation…) | Quantity / Availability. |
| --- | --- | --- |

## 3 - RESOURCE ALLOCATION
Match each activity with what it requires

| Activity | Required Resources | Available / missing | Action required |
| --- | --- | --- | --- |

## 4 – FINAL RESOURCE PLAN
Once gaps are solved, finalise your allocation

| Activity | Final Resources Confirmed | Responsible | Deadline. |
| --- | --- | --- | --- |