# ROLES & RESPONSIBILITIES MATRIX (RACI)

`

## WHY THIS TOOL MATTERS?

## In collaborative projects, misunderstandings often come from unclear roles rather than lack of motivation.

## The RACI matrix helps teams clearly define who does what, who decides, and who needs to be informed.

## For youth workers, educators, and project teams involved in cultural mediation or participatory projects, the RACI matrix:

## clarifies responsibilities within the team,

## avoids duplication of work or forgotten tasks,

## supports smoother collaboration between partners,

## reduces conflicts and frustration,

## strengthens accountability and decision-making.

## A clear distribution of roles makes projects more efficient, inclusive, and easier to manage.

## HOW TO USE IT?

SMART stands for:

- R – Responsible

- The person(s) who do the task.

- A – Accountable

- The person who makes the final decision and ensures the task is completed.

- C – Consulted

- People who give input or expertise before decisions are made.

- I – Informed

- People who need to be kept informed of progress or results.

Steps:

## 1/ List key tasks or activities

## e.g., content creation, workshop facilitation, communication, evaluation).

## 2/ Identify team members or partners

## Include staff, volunteers, artists, youth participants, or external partners.

## 3/ Assign R, A, C, and I for each task

## Each task should have at least one Responsible and one Accountable.

## 4/ Share the matrix with the whole team

## So everyone understands their role and expectations.

## 5/ Update it if needed

## Roles can evolve during the project.

## TIPS

1/ One task = one Accountable person

This avoids confusion and delays.

2/ Don’t overload one person with too many “R” roles

Balance responsibilities to prevent burnout.

3/ Involve young people when relevant

They can be Responsible or Consulted, not only Informed.

4/ Keep the matrix simple

A clear table works better than long explanations.

5/ Use the RACI matrix as a discussion tool

It’s not just administrative — it helps teams talk openly about roles, power, and decision-making.