## Registration and assessment
Matrice di criticità del rischio
Nome del progetto
PROBABILITY
Scala del rischio |  |  |  | Molto basso | Basso | Medio | Forte | Molto forte
Livello 1 |  |  | Impatto |  |  |  |  | R4
Livello 2 |  |  | Molto alto |  |  |  | R1
Livello 3 |  |  | Alto
|  |  | Medio |  |  | R3
|  |  | Basso |  |  | R2
Molto basso
Legenda dei rischi:
| R1: | Spazio non disponibile per il laboratorio
| R2: | Maltempo
| R3: | Risorse IT non disponibili a tempo pieno
| R4: | La domanda di sovvenzione viene rifiutata.
| R5: | …
| R6: | …

## Action level 1
Criticality level 1
List of risks identified at this level:
Risk details | Action to be taken | Time limit | Follow-up on... Date: ../../.... | Follow-up on... Date: ../../.... | Follow-up on... Date: ../../.... | Risk status | Secondary action to be planned. Person in charge | Follow-up
R2: bad weather | Ask the town hall to make a marquee or community hall available. | Awaiting the opening date of the exhibition to the public. | Still no date found. | Date confirmed. Inauguration in three months. Request submitted to the town hall today. | La mairie a accepté la mise à disposition de la salle commThe town hall has agreed to make the community hall available, which is a reserved room.unale, salle réservée. | Risk ended | Louis: Draft a partnership agreement and define the terms and conditions (duration, etc.).. | In progress

## Action level 2
Criticality level 2
List of risks identified at this level:
Risk details | Action to be taken | Time limit | Follow-up on... Date: ../../.... | Risk status | Secondary action to be planned. Person in charge | Follow-up
R3: IT resources not available on a full-time basis. | Obtain a computer and printer. Each project member solicits their network. | Within one month (../../….) to work on the design of the flyers. | Computer and printer lent by a volunteer. | Risk ended | No secondary action is expected.

## Action level 3
Criticality level 3
List of risks identified at this level:
Risk details | Action to be taken | Time limit | Follow-up on... Date: ../../.... | Follow-up on... Date: ../../.... | Follow-up on... Date: ../../.... | Risk status | Secondary action to be planned. Person in charge | Follow-up
R1: Room not available for the manufacturing workshop. | Search for a location with access to toilet facilities, a sink and electrical sockets. Contact local associations and the surrounding community. | Urgent | Loan of premises equipped by an association. |  |  | Risk ended | Louis: Draft a partnership agreement and set out the terms and conditions in writing. | Not started
R4: The grant application was refused. | Launch of a crowdfunding campaign on social media. | Urgent | Crowdfunding campaign launched on ../../…. | Partially achieved (€2,000 raised) Target to be achieved: €5,000 to cover all project costs. | Target exceeded on ../../…. | Risk ended | Lyvia: Thank you post to contributors + contact them by message to offer them a gift, such as a printed T-shirt, a magnet, etc. | In progress

## Annexe
Not started
In progress
Finished